## September 2026
September 2026
Sun | Mon | Tue | Wed | Thu | Fri | Sat
30 Aug | 31 Aug | 01 Sep * National Day | 02 Sep * National Day | 03 Sep Release UAT - 1.14.1 | 04 Sep Release STG | 05 Sep
06 Sep | 07 Sep Release PROD - 1.14.1 | 08 Sep BFF Dress Rehearsal EDT: Sep 8 – 2:59 AM → 8:00 AM PDT: Sep 7 – 11:59 PM → Sep 8 – 5:00 AM ICT: Sep 8 – 1:59 PM → 7:00 PM | 09 Sep Release STG | 10 Sep Winco Dress Rehearsal | 11 Sep Release STG | 12 Sep
13 Sep | 14 Sep BFF Cutover Launch EDT: Sep 14 – 2:59 AM PDT: Sep 13 – 11:59 PM ICT: Sep 14 – 1:59 PM | 15 Sep | 16 Sep Release STG | 17 Sep Winco Cutover Launch | 18 Sep Release UAT - 1.14.2 | 19 Sep
20 Sep | 21 Sep | 22 Sep PCC Dress Rehearsal ICT: Sep 22 – 1:59 PM → 7:00 PM PDT: Sep 22 – 11:59 PM → Sep 23 – 5:00 AM EDT: Sep 23 – 2:59 AM → 8:00 AM | 23 Sep Release STG | 24 Sep | 25 Sep Release PROD - 1.14.2 | 26 Sep
27 Sep | 28 Sep Release UAT - 1.15.1 | 29 Sep | 30 Sep PCC Cutover Launch ICT: Sep 30 – 1:59 PM PDT: Sep 30 – 11:59 PM EDT: Oct 1 – 2:59 AM | 01 Oct | 02 Oct Release STG | 03 Oct

## Release & Events
Date | Day | Event | Details
2026-09-01 | Tuesday | * National Day
2026-09-02 | Wednesday | * National Day
2026-09-03 | Thursday | Release UAT - 1.14.1
2026-09-04 | Friday | Release STG
2026-09-07 | Monday | Release PROD - 1.14.1
2026-09-08 | Tuesday | BFF Dress Rehearsal | EDT: Sep 8 – 2:59 AM → 8:00 AM PDT: Sep 7 – 11:59 PM → Sep 8 – 5:00 AM ICT: Sep 8 – 1:59 PM → 7:00 PM
2026-09-09 | Wednesday | Release STG
2026-09-10 | Thursday | Winco Dress Rehearsal
2026-09-11 | Friday | Release STG
2026-09-14 | Monday | BFF Cutover Launch | EDT: Sep 14 – 2:59 AM PDT: Sep 13 – 11:59 PM ICT: Sep 14 – 1:59 PM
2026-09-16 | Wednesday | Release STG
2026-09-17 | Thursday | Winco Cutover Launch
2026-09-18 | Friday | Release UAT - 1.14.2
2026-09-22 | Tuesday | PCC Dress Rehearsal | ICT: Sep 22 – 1:59 PM → 7:00 PM PDT: Sep 22 – 11:59 PM → Sep 23 – 5:00 AM EDT: Sep 23 – 2:59 AM → 8:00 AM
2026-09-23 | Wednesday | Release STG
2026-09-25 | Friday | Release PROD - 1.14.2
2026-09-28 | Monday | Release UAT - 1.15.1
2026-09-30 | Wednesday | PCC Cutover Launch | ICT: Sep 30 – 1:59 PM PDT: Sep 30 – 11:59 PM EDT: Oct 1 – 2:59 AM
2026-10-02 | Friday | Release STG